## Slide 1
OCB-FF NEOBANK PROJECT
PRE-LAUNCH ROADMAP
7 March 2022

## Slide 2
This document sets out the pre-launch project roadmap based on our experience in launching and scaling neobanks in other markets. The two parties will refine this plan together based on OCB’s and Vietnamese market specifics.
We suggest organising the plan across the following work streams:
Legal & Governance: signing the Partnership agreement, setting up the legal structure and governance
Human Resources: assembling the project team
Product & IT: localising and customising the product/services and the app for the Vietnamese market, integrating with the OCB’s infrastructure / 3rd party vendors
Marketing: developing marketing strategy and preparing the launch campaign and materials
Proposed actions by party and indicative timeline for each the workstreams are discussed on the following pages.
We estimate that it will take us 4-5 months to execute the pre-launch roadmap and go live with the Neobank project.
Summary

## Slide 3
Human Resources
Legal & Governance
Product & IT
Marketing
Timeline
Pre-launch |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Launch |  |  | 
Jan |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  | May |  |  |  | Jun |  |  |  | Jul |  |  |  | Early Aug |  |  | 
W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32
1| MOU
2| Confirmatory DD
4| SA Negotiations & Signing
5| FF VN Incorporation
6| Business Plan Finalisation
3| Governance Setup
7| Project Financing
1| Project team set-up
2| Recruitment and training of local staff
1| IT Audit
3| Back-end Adaptation
2| App UI & Products / Services Customisation
5| Test & Publish
4| Integration with OCB / 3rd Party Vendors
4| Launch Campaign Preparation
3| Marketing Strategy Development
5| Run Pre-Subscribe Campaign
1| Assess Lead Price
6| Design Cards & Print Materials
2| Partnership with
ICS (Visa, MasterCard, JCB)

## Slide 4
Legal & Governance
Pre-launch |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Launch |  |  | 
Jan |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  | May |  |  |  | Jun |  |  |  | Jul |  |  |  | Early Aug |  |  | 
W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32
Task | FF | OCB | Timeline
1¦ MOU Signing | Prepare the MOU outlining key terms of the partnership (operational set-up, role and responsibilities by partner, investment and return split etc) | Agree and sign the MOU | Done
2¦ Confirmatory DD Process | Responses and clarifications to the OCB DD Checklist | Confirm the completion of the legal due diligence | Done
3¦ Governance Setup | Develop principles of management reporting of the project Agree the Steering Committee composition, governance and oversight responsibilities |  | W6 - W10
4¦ SA Negotiations & Signing | Provide draft Service Contract Discuss and agree on the execution version Get corporate approvals for the Service Contract Signing the Service Contract after incorporation of FF VN | Review the draft Discuss and agree on the execution version Get corporate approvals Signing the Service Contract | W10 - W18
5¦ FF VN Incorporation | FFUK corporate approvals (done) Vietnamese authorities' approvals Incorporation |  | W10 - W18
6¦ Business Plan Finalisation | Finalize the 5-year business plan and Year 1 budget based on the refined inputs from marketing, product, IT & Operation workstreams |  | W10 - W14
7¦ Project Financing | FF UK receives approval of the transfer from the servicing bank FF VN registers the loan agreement with SBV (in case of debt financing) FF UK transfers funds to FF VN to finance local Opex & Capex (c.$2m to cover pre-launch and first 3 months of operations) FF UK or FF VN places the guarantee deposit ($3m initially) |  | W17 - W24
1| MOU
2| Confirmatory DD
4| SA Negotiations & Signing
5| FF VN Incorporation
6| Business Plan Finalization
3| Governance Set-up
7| Project Financing

## Slide 5
HR
Pre-launch |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Launch |  |  | 
Jan |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  | May |  |  |  | Jun |  |  |  | Jul |  |  |  | Early Aug |  |  | 
W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32
Task | FF | OCB | Timeline
1¦ Project team | Parachute the FF core project team (key business leads) to Vietnam to kick-start execution of the pre-launch plan Assist OCB in mobilising/hiring the Neobank project team from OCB side - could be from the Bank’s existing employees or external candidates. Propose compensation packages for the Neobank team | Mobilise internally / hire externally the Neobank project team from OCB side | W10 – W14
2¦ Recruitment and training of new local staff | Arrange for employment agreements between the local hires and the FF VN / OCB |  | W15 – W24
1| Project team set-up
2| Recruitment and training of new local staff

## Slide 6
Pre-launch |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Launch |  |  | 
Jan |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  | May |  |  |  | Jun |  |  |  | Jul |  |  |  | Early Aug |  |  | 
W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32
Product & IT
Task | FF | OCB | Timeline
1¦ Conduct IT Audit | Software & Hardware audit Prepare Infrastructure and integration flowcharts Setup Software to Hardware according to the flowcharts | Provide the required materials Prepare Hardware according to the flowcharts | W9 - W11
2¦ App Customization | Customise UI/UX and workflows | Approve UI/UX and workflows | W13 - W24
3¦ Backend Adaptation | Integrate API Layer with OCB / 3rd party vendors Customise Business Logic in processes |  | W13 - W24
4¦ Integration with OCB / 3rd Party Vendors | Core banking Processing Payment systems etc. Contract with CIC and other data providers | Prepare necessary APIs/documentation | W13 - W24
5¦ Test & Publish Neobank App | Functional testing Regression testing UAT Security testing Open an account and publishing on App Store & Play Google |  | W25 - W28
1| IT Audit
3| Back-end Adaptation
2| App UI & Products / Services Customization
5| Test & Publish
4| Integration with OCB / 3rd Party Vendors

## Slide 7
Onboarding
Task | FF | OCB | Timeline
1¦ Customer T&Cs | Develop and approve a standard customer agreement (terms and conditions) |  | W10 - W13
2¦ Registration Process | Assess and prepare a package of documents required for opening an account (KYC, AML etc.) Internal filing system Create interfaces and services for the credit card issuance |  | W10 - W13
3¦ On-boarding Design | Develop design of the onboarding flow | Approve the design | W13 - W16
4¦ Integration with Core Banking & Processing | Integrate with the OCB core banking and processing system allowing to create a customer, a card, an account | Provide APIs for integration Assist with integration | W17 - W24
5¦ Integration with Other On-boarding Services | Integrate with other services for the on-boarding process: SMS-service, documents validation, addresses directory, KYC service etc. |  | W17 - W24
Pre-launch |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Launch |  |  | 
Jan |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  | May |  |  |  | Jun |  |  |  | Jul |  |  |  | Early Aug |  |  | 
W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32
3| On-boarding Design
2| Registration Process
4| Integration with Core Banking & Processing
1| Customer T&C
5| Integration with other Onboarding Services

## Slide 8
Payments
Task | FF | OCB | Timeline
1¦ Payments Services Localization & Integration | Deep dive into the local payments market and services (utilities, phone top up, internet etc.) Understand the Bank’s existing payment services Localise our payment services and integrate with the Bank’s / selected 3rd party services | Provide API for integration Fine tune the Bank’s processing for our services Assist with integration | W11 - W16
2¦ P2P Service | Localise our P2P payment service and integrate with the Bank’s P2P service |  | 
 |  |  | W11 - W14
3¦ Payments Design | Localise payments flow design |  | W18 - W21
4¦ Card Top-up | Analyse the Bank’s existing card top up services (cash in, ATM) Localise our top up process and integrate with the Bank’s services |  | 
 |  |  | W18 - W24
Pre-launch |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Launch |  |  | 
Jan |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  | May |  |  |  | Jun |  |  |  | Jul |  |  |  | Early Aug |  |  | 
W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32
3| Payments Design
2| P2P Service
4| Card Top-up
1| Payments Services

## Slide 9
Task | FF | OCB | Timeline
1¦ Loyalty Schemes Localization | Deep dive into local specifics of loyalty schemes including cashbacks Localise our loyalty schemes accordingly Describe cashbacks accrual algorithm | Approve the loyalty schemes | W10 - W13
2¦ Loyalty Schemes Integration with OCB | Integrate the loyalty schemes with the OCB’s services | Assist in integration | W14 - W24
Pre-launch |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Launch |  |  | 
Jan |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  | May |  |  |  | Jun |  |  |  | Jul |  |  |  | Early Aug |  |  | 
W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32
Loyalty Schemes
2| Loyalty Schemes Integration with OCB
1| Loyalty Schemes

## Slide 10
Task | FF | OCB | Timeline
1¦ Credit Product Localization | Deep dive into local specifics of credit product characteristics and associated regulatory requirements Assess external data sources (credit bureau, 3rd party data providers etc.) Understand the current credit decision-making process at OCB Develop our credit product passport (terms, tariffs etc.) | Provide relevant information and documentation Approve the credit product passport CBS & processing settings | W11 - W15
2¦ Credit DMS Prototype Building | Build credit Decision Making System (DMS) prototype (flow charts of the on-boarding questionnaire, background checks etc.) | Provide supporting information Approve DMS prototype | W12 - W18
3¦ Scoring Model Building | Analyse existing customer dataset of OCB Engineer model features (credit predictors) Develop and validate the scoring model (machine learning) | Provide OCB customer data for the model training | W12 - W18
4¦ Credit Limits | Prepare credit limits management strategy | n/a | W18 - W21
5¦ DMS Development | Develop DMS Integrate scoring model with DMS | Develop APIs to provide input DMS data (e.g. black list checks) | W18 - W24
Pre-launch |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Launch |  |  | 
Jan |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  | May |  |  |  | Jun |  |  |  | Jul |  |  |  | Early Aug |  |  | 
W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32
Credit Products & Credit Decisions
1| Credit Product Localization
2| Decision-Making System (DMS) Prototype Building
4| Credit Limits
3| Scoring Model Building
5| DMS Development

## Slide 11
Pre-launch |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Launch |  |  | 
Jan |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  | May |  |  |  | Jun |  |  |  | Jul |  |  |  | Early Aug |  |  | 
W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32
Task | FF | OCB | Timeline
1¦ Card Production | Select payment system provider (Visa/MasterCard/local) Select card manufacturer Design the card and packaging Produce cards | Approve the payment system provider Integrate with the card manufacturer and run card tests Arrange a card warehouse space | W09 - W19
2¦ Card Packaging & Logistics | Develop card order and packaging processes | Arrange packaging premises | W17 - W23
3¦ Card Delivery | Analyse the local delivery market and adjust our card delivery process Integrate with the Bank’s services (documents archiving etc.) | Assist in integration with the Bank’s services Select a 3rd party delivery service (e.g. post) | W10 – W26
4¦ Courier Team Building | Localise our courier communication interface Develop and agree the organisational structure and staffing of courier team Develop remuneration system and training programs Recruit and train the team | Approve the team structure, remuneration and training programs On-board personnel | W15 - W24
5¦ Points of Card Issuance | Consider setting up points of cards issuance (in addition to couriers) leveraging the Bank’s branch network / externally Customise card issuance interfaces Develop remuneration system & training programs for card issuance officers, train the team | Agree customer service processes and integrate into the Bank’s branches | W10 - W24
Card Production & Distribution
2| Card Packaging & Logistics
3| Card Delivery
1| Card Production
4| Courier Team Building
5| Points of Card Issuance

## Slide 12
Task | FF | OCB | Timeline
1¦ Physical Set-up | Prepare and agree on the requirements for the Contact Centre (CC) set up (premises, furniture, equipment etc.) | Provide Bank’s premises / help identifying external premises for the Contact Center, assist with the PPE procurement | W10 - W12
2¦ Customer Communication Channels | Prepare technical specifications and proposals for telephony Set up business flow for telephony communication and a recording system Set up chat and messenger business flow and module Set up customer request processes (validation, underwriting, Help Desk, transaction monitoring, etc.) | Purchase telephony licenses, provide servers and capacities for communication channels and communication recording | W12 - W16
3¦ Work Interfaces | Develop work interfaces for the Contact Centre departments (incoming customer queries, sales, soft collection etc.), integrate them OCB | Assist with integration | W18 - W21
4¦ CC Team Building | Develop and agree the organisational structure and staffing of the Contact Centre, recruit the team Develop remuneration system |  | W12 - W16
5¦ Training and Motivational Programs | Develop training, rating and motivation programs, work quality controls | Approve the programs | W18 - W24
6¦ Readiness Testing | Test chat, calls, validation requests, underwriting, monitoring operations, recorded calls, interfaces etc. |  | W23 - W28
Pre-launch |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Launch |  |  | 
Jan |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  | May |  |  |  | Jun |  |  |  | Jul |  |  |  | Early Aug |  |  | 
W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32
Contact Centre
3| Work Interfaces
2| Customer Communication Channels
4| CC Team Building
1| Physical
Set-Up
5| Training and Motivational Programs
6| Readiness Testing

## Slide 13
Task | FF | OCB | Timeline
1¦ Fraud Detector Rules | Agree list of fraud settings and prepare fraud detector rules: Fraud rules and detectors (Central Bank, Payment System restrictions) Processing limits Card settings (ICC, contactless, ATM etc.) | Provide Bank’s inputs for fraud settings and fraud detector rules | W10 - W13
2¦ ACS Page Customisation | Develop design Prepare 3DS authentication flow | Approve design Agree flow with the Bank’s processing Customise the ACS page | W13 - W23
3¦ Anti-Fraud System Localisation | Customise Anti-fraud expert system for individual fraud rules and limits in line with the local market practice | n/a | W13 - W17
4¦ Anti-Fraud Integration with Processing | Prepare integration protocol for rules and limits check system | Integrate with the Bank’s processing | W18 - W23
5¦ App for Anti-Fraud System Customisation | Integrate and customise our app for the antifraud decisions | n/a | W18 - W24
6¦ Testing | Functional testing Logical testing |  | W25 – W28
Pre-launch |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Launch |  |  | 
Jan |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  | May |  |  |  | Jun |  |  |  | Jul |  |  |  | Early Aug |  |  | 
W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32
Anti-fraud
3| Anti-Fraud System Localisation
2| ACS Page Customization
4| Anti-Fraud Integration with Processing
1| Fraud Detector Rules
5| App for Anti-Fraud System Customisation
6| Testing

## Slide 14
Task | FF | OCB | Timeline
1¦ Assess Lead Price | Make a landing page with information about our neobank (the brand will be temporary) and buy some traffic to it to get a rough understanding of the potential lead price Our further business case discussions may be based on this experiment | n/a | Done
2¦ Partnership with ICS | Select and arrange for partnership with ICI (Visa, MasterCard, JCB) |  | W10 - W16
3¦ Marketing Strategy Development | Engage a marketing agency and conduct a market survey to better understand customer preferences and confirm product features and terms Develop and approve marketing strategy Design branding and mascot |  | W10 - W18
4¦ Prepare Launch Campaign | Prepare launch campaign Produce video materials featuring the new brand for social media and YouTube, visual materials (banners etc.) for the campaign Consider engaging an advertising agency for media planning Set up social network accounts and other marketing channels |  | W19 - W26
5¦ Run Pre-Subscribe Campaign | Set up the website (wait list subscription, card pre order etc.) Run pre-subscribe campaign (social media, banners, performance digital marketing). This campaign will be targeted at early adopters; these pre-subscribers will be the first to get a beta invitation upon launch |  | W21 - W28
6¦ Produce Cards and Print Materials | Design card and print materials (stickers, card envelopes, brochures etc.) Select a third-party provider and order print materials | Approve card design and print materials | W19 - W26
Pre-launch |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Launch |  |  | 
Jan |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  | May |  |  |  | Jun |  |  |  | Jul |  |  |  | Early Aug |  |  | 
W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32
Marketing
4| Launch Campaign Preparation
3| Marketing Strategy Development
5| Run Pre-Subscribe Campaign
1| Assess Lead Price
6| Design Cards & Print Materials
2| Deal for Partnership with
ICS (Visa, MasterCard, JCB)